## Risk Assessment
RISK ASSESSMENT
Code | EN
Version | 1
Created By | Vaishnavi Deshpande
Approved By
Asset No | Asset Name | Owner | Threat | Vulnerability | Likelihood | Impact | Risk Level | Risk ID | Control (Annex A Ref) | Status
1 | Customer Data | Data Protection Officer | Unauthorized Access | Weak Password Policy | High | High | Very High | RSK-001 | A5.17 (Authentication Information) | In Progress
2 | Network Infrastructure | Network Administrator | DDOS Attack | No anti-DDOS measures | High | High | Very High | RSK-002 | A13.1.1 (Network Controls) | Implemented
3 | Employee Laptops | IT Administrator | Theft | No device encryption | Medium | High | Medium | RSK-003 | A8.11 (User Endpoint Devices) | Implemented
4 | Internal file server | IT Security Team | Ransomware | No endpoint protection | High | High | Very High | RSK-004 | A12.2.1 (Malware Protection) | Implemented
5 | Physical Premises | Admin Office | Fire | No Fire suppresion system | Medium | High | Medium | RSK-005 | A11.1.4 (Physical Protection) | In Progress
6 | HR System | IT Security Team | Insider Threat | Excessive Access Rights | High | Medium | High | RSK-006 | A5.8 (Privileged Access rights) | Planned
7 | Web Application | Application Dev Lead | SQL Injection | Input fields not sanitized | High | High | Very High | RSK--007 | A14.2.5 (Secure Coding Practices) | Planned
8 | Cloud Storage | Cloud Admin | Data Leak | Misconfigured Access rights | High | High | Very High | RSK-008 | A5.18 (Access Rights) | Planned
9 | Email System | IT Security Team | Phishing Attack | Untrained users | Medium | High | High | RSK-009 | A7.2.2(Information Security Training) | In Progress
10 | Backup server | IT Administrator | Hardware Failure | No offsite backup | High | High | Very High | RSK-010 | A12.3.1 (Information Backup) | Implemented

## Risk Treatment
Risk Treatment
Treatment Plan Ref | Risk Description | Control ID | Control Name | Treatment Option | Mitigation Action | Risk Treatment Owner | Start Date | Deadline | Status
TTP-001 | Unauthorized access due to weak authentication | A 5.17 | Authentication Information | Mitigate | Implement MFA and stromg password policies | IT Security | 2025-01-01 | 2025-01-02 | In Progress
TTP-002 | DDOS attack | A 8.20 | Network Controls | Mitigate | Firewalls, Network segmentation, VPN, IDS/IPS | Network Lead | 2025-10-01 | 2025-10-02 | Implemented
TTP-003 | No device encryption | A 8.11 | User Endpoint Devices | Mitigate | Formal Cryptographic Policy to be developed. TLS, AES Encryption and key management to be used for file storage and backups. | IT Security | 2025-12-01 | 2025-05-02 | Implemented
TTP-004 | Ransomware attack | A 12.2.1 | Malware protection | Mitigate | Anti-Malware software to be deployed on all endpoints, automatic updates enabled, email filtering, user training and USB control policies to be put in place. | IT Security | 30-01-2025 | 2025-01-03 | Implemented
TTP-005 | Unauthorized physical access, No fire suppression ssytem | A 11.1.4 | Physical Protection | Mitigate | CCTC, Access cards, Visitor logs | Admin Lead | 2025-02-01 | 2025-03-02 | Implemented
TTP-006 | Admin access misuse on HR system | A 5.8 | Privileged Access Rights | Mitigate | Apply least privilege and implement PAM | IT Infra Manager | 15-02-2025 | 15-03-2025 | Planned
TTP-007 | Input fields not sanitized | A 14.2.5 | Secure Coding Practices | Mitigate | Secure coding standards, code review, DevSecOps in CI/CD | DevSecOps Lead | 2025-10-01 | 2025-03-02 | Planned
TTP-008 | Excessive or outdated user access to Cloud storage | A 5.18 | Access Rights | Mitigate | Implement RBAC, Conduct quarterly access reviews | Cloud Admin | 2025-11-01 | 2025-11-02 | Planned
TTP-009 | Lack of employee awareness on phishing | A 7.2.2 | Information Security Training | Mitigate | Phishing simulations, email banners, security onboarding, annual training | Security Awareness Lead | 2025-04-02 | 2025-03-03 | In Progress
TTP-010 | Loss or tampering of backup data | A 12.3.1 | Information Backup | Mitigate | Encrypt backup files, verify integrity and set retention policies | IT Infrastructure Lead | 2025-02-01 | 2025-03-03 | Implemented